CORE COMPONENTS

|  | F 10 | S 11 | Sum 11 | F 11 | S 12 | Sum 12 | F 12 | S 13 | Sum 13 | F 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| First Year Seminar (FYS) and Academic & College Success (ACS) | - Pilot discip. FYS with lab and assess - Chairs & faculty approached for F11 - Chairs schedule 10 sections for F11 | - CCC with CFYS & faculty develops FYS and ACS criteria - Criteria to faculty 2/18 - Faculty vote 3/25 | - Grants, PD | - 10 sections of FYS & ACS offered (create and preserve artifact in each—paper?) - Chairs schedule 25 sections for F12 (2-3 in each area) | - Proposals for F12 submit 1/15 - Proposals approved 2/15 - PD - Assessment of 9 sections of fall 2011 pilots | Grants, PD | - 25 sections (100%) of FYS & ACS offered (create and preserve artifact in each) - Chairs schedule 25 sections for F13 | - Proposals for F13 submit 1/15 - Proposals approved 2/15 | Grants, PD | - 25 sections of FYS & ACS offered |
| Perspectives-Enduring Questions (P-EQ) |  | - CCC with input (faculty, WAC, etc.) develops P-EQ criteria & procedures - Criteria to faculty 2/18 - Faculty vote 3/25 - Chairs schedule 20 sections for S12 (goal 25% of total PIs—2-3 sections in each area) | - Grants, PD - Props for S12 submit 8/18 | - Proposals for S12 approved 9/15 - Chairs schedule 40 sections for F12 (goal 50%)—5 sections in each area | - Pilot initial P-EQ offerings (25%) (create and preserve artifact in each) - Proposals for F12 submit 1/15 - Proposals approved 2/15 -Chairs schedule 60 sections for S13 (goal 75%)—7-8 sections in each area | Grants, PD - Props for S13 submit 8/18 | - Proposals for S13 approved 9/15 - 40 P-EQ sections offered (50%) (create and preserve artifact in each) - Chairs schedule 80 sections for F13 (100%)—10 sections in each area | - 60 P-EQ sections offered (75%) - Proposals for F13 submit 1/15 - Proposals approved 2/15 | Grants, PD - Props for S14 submit 8/18 | - Proposals for S14 approved 9/15 - 80 P-EQ sections offered (100%) - Chairs schedule 80 sections for F14 (100%)—10 sections in each area |
| Integrative Studies (IS) |  | - CCC with input (faculty, WAC, etc.): Begin meaningful conversation about models of IS - CCC, Chairs & Faculty begin discussions about possible IS clusters |  | - CCC, Chairs & Faculty identify possible clusters as models - CCC develops criteria for IS - Criteria to faculty - Faculty vote - CCC develops timeline for pilots & implementation | Faculty develop IS Clusters via wiki | -Wiki closed; info processed | - CCC reviews IS Clusters, discusses IS Clusters to launch first, logistics, dept impact, etc. - CCC continues to receive IS Cluster ideas | - CCC determines best way to advertise IS Clusters - CCC reviews new IS Cluster ideas |  |  |
| Core Milestone Experience (CME) |  | - CCC with input (faculty, WAC etc.): Begin meaningful conversation on models of CME - CCC considers 1-credit course as CME |  | - CCC develops criteria for ISS - Criteria to faculty - Faculty vote | - CCC develops goals and syllabus of CME | PD |  | - Pilot CME? | - Assess pilot |  |
| Portfolio at Nazareth (P@N) | - ITS explores software | - ITS explores software with input (CCC, FYS pilot, AC, etc.) - Pilot I-Webfolio | - Assess pilot | - Pilot II: group looks at software - CCC & ITS narrow down software options - Make decision | - Sign Contract - April workshop for Alpha group which sets up standards & rubrics | -Alpha teaches Beta | - Pilot P@N in selected FYS - CCC continues to work on structure | - Assess software - Alpha & Beta teach Gamma - Delta Force (students) trained to help others |  | - Full use of P@N in all FYS and P-EQ sections |
| Experiential Learning (EL) |  | - CCC with input: Begin meaningful conversations about what counts as EL: who administers it, who assesses reflection, etc. |  | - EL Steering Committee formed - Develops ‘Characteristics of EL’ document | - CCC reviews document - ELSC makes revisions to doc, works on coordination, etc |  | - ELSC moves into implementation mode (common SLOs, etc) | - ELSC implements common SLOs |  | - All incoming students able to plan their EL |
| Health & Wellness |  |  |  | - Health & Wellness Committee formed | - H&W Com develops criteria - CCC reviews criteria |  | - H& W implemented as pilot | - Review pilot |  | - All incoming students able to plan and schedule their H&W |
| Transitional Issues | - Elect CCC - Appoint Director of Core Curriculum -Liberal Arts Sub-committee ends | - New PI proposals accepted from new faculty - New PII proposals go to CCC - ‘Articulation of Transition’ developed |  | - Articulation of Transition approved |  |  |  |  |  | - P(EQ) fulfill old PI requirement |

ADMINISTRATION

|  | F 10 | S 11 | Sum 11 | F 11 | S 12 | Sum 12 | F 12 | S 13 | Sum 13 | F 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Core Director | - Appointed - Finalize Timeline (take to constituents, and faculty 11/19 & 12/3) - Initiate discussion of Core Components with CCC - Oversee FYS pilot - Talk to departments & faculty | - Lead development of FYS, ACS, P-EQ criteria, and discussions of models of IS, CME & EL - Initiate cross-disciplinary discussions of possible IS clusters - Develop PD procedures - Coordinate discussion of transfer student core - Coordinate discussion of 'Articulation of Transition' (from old to new core) | - Lead PD - Core Baseline Report | - Coordinate E-Portfolio assessment and software choice - Lead finalization of criteria for IS, CME, & IS clusters - Lead discussions of EL criteria - Coordinate assessment of pilots, etc. - Lead CAS Chairs discussion of Core impact on Majors, 8 area SLO coordination & rubrics & transfer credit issues - work on Articulation agreements - Publicity (Admissions, create Core Website) - Lead PD - Create IS Cluster wiki | - Initiate conversation about Health & Wellness - Coordinate assessment of pilots (FYS & ACS) - Coordinate wiki IS clusters - Lead discussion of CME - Work on Assessment Rubric for Core Components - Coordinate new course approval and CARFs - Member of AC - Grants Commit. - PD - Co-chair ELSC - Alpha for P@N - Complete report for MiddleStates - update Web & marketing - Admissions work | - Lead PD - wiki - P@N - assess S-12 P-EQs | - Coordinate assessment of pilots (S-12 P-EQ) - Coordinate IS Clusters - Core Rubrics - New Course approvals - Member of AC - PD - Co-chair ELSC - Alpha for P@N - Web, Marketing and Admissions - Refine Core procedures and criteria - Finalize CME design with CCC - Begin creation of Transfer Student Orientation Workshop - Coordinate rewriting of Articulation Agreements | - Coordinate assessment of pilots - Refine procedures and criteria - Member of AC - PD - Co-chair ELSC - Alpha for P@N - Web, Marketing and Admissions - Coordinate IS Clusters - Core Rubrics - New Course approval | - Lead PD | - Coordinate assessment of pilots - Refine procedures and criteria - Member of AC - PD - Co-chair ELSC - Alpha for P@N - Web, Marketing and Admissions - Coordinate IS Clusters - Core Rubrics - New Course approval |
| Core Curriculum Committee (CCC) | - Elected - Initial conversations about FYS, ACS and P-EQ criteria - Finalize Timeline | - Develop FYS & ACS criteria - Develop P-EQ criteria & procedures - Criteria to faculty 2/18 - P-EQ, FYS & ACS criteria to faculty 2/18 - Begin conversations about IS and CME - Begin conversations about EL - Discuss 'Articulation of Transition' - Backwards design of Portfolio - Assess and report on FYS pilot from F 2010 | - Receive S12 P(EQ) props. 8/18 | - Approve S12 P-EQ proposals 9/15 - Develop IS and CME criteria - Develop IS implementation timeline - Give input for ePortfolio software - Receive and comment on Characteristics of EL from ELSC | - Receive F12 P-EQ, FYS & ACS proposals 1/15; Approve 2/15 - Begin conversations about Health & Wellness - Assess and report on Fall pilots - Design CME | - Receive S13 P-EQprops. 8/18 | - Approve S13 P-EQ proposals 9/15 - Finalize criteria for Health and Wellness - Assess and report on Spring pilots - Discuss CME and IS Clusters | - Receive F13 P-EQ, FYS & ACS proposals 1/15; Approve 2./15 - Assess and report on Fall pilots - Receive proposals for new IS Clusters | - Receive S14 P-EQ props. 8/18 | - Approve S14 P-EQ proposals 9/15 - Assess and report on Fall pilots - Receive proposals for new IS Clusters |
| Chairs | - Schedule 10 sections of FYS for F11 | - Schedule 20 sections of P-EQ for S12 (goal 25% of total PIs), 2-3 in each area - Determine impact of new core on major requirements - Lead departmental discussions about development of FYS, P-EQ courses & possible IS clusters - Discuss 'Articulation of Transition' |  | - Schedule 25 sections (100%) of FYS (3 in each area) and 40 sections (50%) of P-EQ for F12, 5 sections in each area - Continue departmental discussions about development of FYS, P-EQ & possible IS clusters, SLO coordination | - Schedule 60 sections (75%) of P-EQ for S13, 7-8 sections in each area - Identify SLOs of Senior Seminars - Continue departmental discussions about development of FYS, P-EQ courses & possible IS clusters - finalize wiki in May |  | - Schedule 25 sections of FYS and 80 sections (100%) of P-EQ for F13, 10 sections in each area | - Schedule (80) sections (100%) of P-EQ for S14, 10 sections in each area |  | - Schedule 25 sections of FYS and 80 sections (100%) of P-EQ for F14, 10 sections in each area |
| Registrar | - F11 overview due Dec 1 - Schedule 10 sections of FYS and ACS for F11 - Build FYS & ACS into current degree audit | - S12 overview due May 1 - 25% P-EQ scheduled on S12 overviews. - Review degree audit structure - Identify what will be tracked with degree audit and how. |  | - F12 overview due Dec 1 - Convert all remaining FRS to FYS for F12 - Continue work on degree audit (differentiate FYS and P-EQ) - Naznet & Catalog | - S13 overview due May 1 - Work on tracking EL requirement |  | - F13 overview due Dec 1 - Update current and new degree audit for all P-EQ approved for F13 | - S14 overview due May 1 |  | - Degree audit for new core in place for incoming 1st year students |
| Advisement |  | -Revise degree audits to accept new courses into old core - Discuss 'Articulation of Transition', & document policies and develop tools on how new courses will count towards old core (with Chairs and CCC) |  | - Articulation Agreements - Failure Policy | - Transfer students | -Develop tools for advisors/ students -Develop process & forms for IS and EL |  | - Lead January Faculty Assembly Day: "The New Core & Advisement", i.e., degree audit, transfer policies, IS, EL, portfolios, etc. - Send new Advising Tools to incoming students |  |  |
| Transfer Students | - Begin conversations about modified core & articulation agreements - Begin to develop transfer credit policies for new core | - Begin to re-write articulation agreements with 2 year schools |  |  | - Begin discussions about orientation workshops (Who will oversee and teach these?) |  | - Plan orientation workshops for F13 | - Evaluate new F13 transfer students for new core |  | - Orientation workshops to this core curriculum |
| Assessment Committee |  | - Act as consultant for portfolio design - Act as consultant for Core SLO refinement |  | - Act as consultant for pilot assessments | - Act as consultant for pilot assessments |  | - Act as consultant for pilot assessments | - Act as consultant for pilot assessments |  |  |
| Professional Development |  | - WAC workshops on informal writing strategies | P-EQ and FYS | - E-Portfolio - WAC - P-EQ - FYS - Critical Thinking | - P@N - WAC - P-EQ - FYS - Critical Thinking - Reflection | - FYS | - P@N - WAC - P-EQ - FYS - Critical Thinking - Reflection | - Faculty Assembly Day: "The New Core & Advisement" - P@N, WAC, P-EQ, FYS, etc. | Adv. | - P@N, WAC, P-EQ, FYS, etc. |
| Admissions | - Begin to brainstorm about 'Talking Points' for the marketing of the new core | - Develop new communication materials - VP Admissions communicates with Core Director for faculty input | - Work on com. materials | - Communication materials to production 09/01 - Presentation to Ambassadors by Core Director | - 01/01 Begin to actively recruit students for F13 - Presidential Scholars program - Reflection discussions |  | - New Core in Exp Naz days - Active recruitment | - New Core in Exp Naz days - Active recruitment |  | - New Core in Exp Naz days - Active recruitment |
| Budget consideration |  |  | PD Director | PD | PD | PD Director | PD | PD | PD Director | PD |